## roadmap
roadmap
Name | Status | Timeline - Start | Timeline - End | Estimation | Link to Blank Board | Release date
design user-item DB
Design relational user/client and item/product DB |  | 2020-06-29 | 2020-06-30 | 2 | release 1 | 2020-07-22
|  | 2020-06-29 | 2020-06-30 | 2
Login UI
Build a login UI |  | 2020-07-01 | 2020-07-02 | 2 | release 1 | 2020-07-22
|  | 2020-07-01 | 2020-07-02 | 2
Registration microservice
Implement the service based on email |  | 2020-07-03 | 2020-07-06 | 2 | release 1 | 2020-07-22
Add possibility to register based on SSO |  | 2020-08-12 | 2020-08-18 | 5 | release 3 | 2020-09-25
|  | 2020-07-03 | 2020-08-18 | 7
Authentication microservice
Implement the service and add OAuth 2.0 method |  | 2020-07-07 | 2020-07-09 | 3 | release 1 | 2020-07-22
Design and develop Unit Tests |  | 2020-07-10 | 2020-07-10 | 1 | release 1 | 2020-07-22
|  | 2020-07-07 | 2020-07-10 | 4
Search microservice
Implement simple search service - word much |  | 2020-07-13 | 2020-07-15 | 2 | release 1 | 2020-07-22
Add advanced search |  | 2020-07-20 | 2020-07-23 | 4 | release 2 | 2020-08-18
Design and develop Unit Tests |  | 2020-07-16 | 2020-07-16 | 1 | release 1 | 2020-07-22
|  | 2020-07-13 | 2020-07-23 | 7
Setup CI/CD
Setup CI as a checkin criteria based on unit tests |  | 2020-07-17 | 2020-07-17 | 1 | release 1 | 2020-07-22
Implement end-to-end complex tests for release criteria |  | 2020-07-24 | 2020-07-24 | 1 | release 2 | 2020-08-18
|  | 2020-07-17 | 2020-07-24 | 2
Cart/basket microservice
Implement the service responsible for collecting available items |  | 2020-07-27 | 2020-07-31 | 5 | release 2 | 2020-08-18
|  | 2020-07-27 | 2020-07-31 | 5
Payment microservice
Implement the service responsible for payment |  | 2020-08-03 | 2020-08-07 | 5 | release 2 | 2020-08-18
Add possibility to use all known/common payment methods |  | 2020-08-19 | 2020-09-04 | 13 | release 3 | 2020-09-25
Design and develop Unit Tests |  | 2020-08-10 | 2020-08-11 | 2 | release 2 | 2020-08-18
|  | 2020-08-03 | 2020-09-04 | 20
Order/delivery microservice
Implement the service responsible for prepare/send request to deliver companies |  | 2020-09-07 | 2020-09-18 | 10 | release 3 | 2020-09-25
|  | 2020-09-07 | 2020-09-18 | 10
Client activity tracking microservice
Implement the service to track activity, keep history |  | 2020-09-21 | 2020-09-25 | 5 | release 4 | 2020-10-23
Analyze activity and suggest appropriate items to client |  | 2020-09-28 | 2020-10-02 | 5 | release 4 | 2020-10-23
Design and develop unit tests |  | 2020-10-05 | 2020-10-07 | 3 | release 4 | 2020-10-23
|  | 2020-09-21 | 2020-10-07 | 13
Improvements
Design Redis DB for client session management |  | 2020-10-08 | 2020-10-15 | 6 | release 4 | 2020-10-23
|  | 2020-10-08 | 2020-10-15 | 6
Done
Name | Status | Timeline - Start | Timeline - End | Estimation | Link to Blank Board | Release date